Closeout Report: / Tablet Rollout`

# Project Summary
- briefly describe the project
- explain the desired results,
- including some of the key success criteria.

Purpose(goal/Aim), scope, duration: The implementation of introducing a tablet for customer project aimed to provide the customer with a modern application food menu, order selection and card checkout having the primary objectie to improve the overall cusotmer service efficiency.

The duration for the project was 10 months.it is commenced on April 30, 2023 and cocluded on 10th November 2023.

The key objectives expected was,

1. Reduce the table turn time to 30 minutes.
2. Average table checkout time to one minute or less.
3. Clear messaging around payment options such that make it clear tablets only take cards while streamlining the customers who wants to pay cash.
4. Less than 5% of customers reporting tech issues each week
5. Increase Daily Guest count by 10%
6. Reduce food waste by 25%

Project Milestones
1. Project Kickoff: January 15, 2023
2. planning and Approval: March 1, 2023
3. Content Finalization: April 15, 2023
4. Development Completion: December 15, 2023
5. Testing and QA: January 15, 2024
6. Final Launch: May 30, 2024

Budget and Expenditure
- Initial Budget: $150,000
- Total Expenditure: $145,000
- Budget Variance: -$5,000
The project was completed within budget, saving $5,000.
After a test launch and wait staff training, we could achive all above objectives successfully while wining the daily guest count by 20% based on survey in return to the 10% expectation.
Positive feedback received from users and stakeholders regarding the tablet usability and application design.

# Methodology
The tablet software development followed up the SCRUM Agile process.

# Results
Performance Baseline:
	Planned	Actual	Notes
Actual Project Schedule vs Planned	Launch on Apr. 23	Launched on Apr. 23	We were able to launch on the day we wanted, but had to accelerate our tasks due to delays
Actual Project Cost vs Planned	Training materials and fees: $10,000 / Hardware and software implementation across locations: $3,500 / Maintenance (IT fees): $5,000 / Updated website and menu design fee: $5,000 / Other customization fees: $550	Training materials and fees: $7,486 / Hardware and software implementation across locations: $3,600 annually / Maintenance (IT fees): $0 (included with hardware order subscription) / Updated website and menu design fee: $4,250 / Other customization fees: $578	Overall, we nearly matched our budget
Planned Scope vs Delivered Scope	Install tablets at two restaurant locations / Launch at the beginning of Q2 (April 1) / Create a plan for how to train staff on the new system	Physically installed tablets at two restaurant locations via electrician / Added menus, coupons, branding, and additional content to tablets / Integrated tablets with POS system / Negotiated with tablet vendor over timing / Created a plan for training / Managed waitstaff expectations and concerns / Trained BOH and FOH / Created system for maintenance/locking / Implemented system of surveying and measuring customer satisfaction	We didn’t realize how many moving pieces we were going to encounter

Key Accomplishments:
- Improved daily guest count by 20%.
- Positive feedback received from users and stakeholders regarding the tablet usability and application design.
- Successfull training wait staff memebers
- User engagement metrics improved by 30%, indicating successful integration of interactive features
- User positive expeince with tablet were arount 70% with or without waiter, indicating successfulness of the move taken by the project.
# Lessons Learned
What were the things went well and what not and what can be done/Actions?
- Continuous Training of waitstaff ois required until many customers are fmiliar with the tablet
- Getting continous feedback from customers to improve further
- Effective Communication: Regular updates and open communication channels between the project team and stakeholders were crucial for timely issue resolution and project success.
- Adequate Testing: Allocating sufficient time for testing and quality assurance ensured a smooth and error-free website launch.
- Flexibility in Planning: Being flexible and adaptable in the project plan helped accommodate unforeseen changes and challenges without impacting the project timeline.
# Next Steps
1. There is no ongoing development for Project application though improvement/maintance should be carried out in next projects
2. more Regression testing of the application should be carried out
3. There are no Open action items from the planning ramins for this project
4. There is a risk of not reciving ordered food for 28% customers and this should be addressed asp in next quarter.
5. Moving forward, Molly will take care of the project (Own) for the location A, as a PM.

# Project Documentation Archive
for future project managers or stakeholders to reference
- [link the project proposal]
- [link the project charter] – highlevel project plan overview ,Project approval document from stakeholders
- [link the project plan] - It includes timelines, milestones, deliverables, and dependencies, as well as the roles and responsibilities of each team member.
- [link the evaluation findings presentation]